## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Overall tablet experience | 72% of customers rated their overall experience with the tablet with 4 or 5 | Continue implementing what worked, focus on improving based on customer feedback, and continue surveying customers to keep finding improvement opportunities and identifying what works
|  |  | 40% of customers liked the tablet experience better, and want to use it exclusively going forward | Continue offering the tablet experience and start implementing this system in other Sauce & Spoon locations
Customers | Went well | Waiter instructions on how to use the tablet | 76% of customers stated that their waiter instructed them very well on how to use the tablet | Congratulate the waiters and continue training them on best practices for instructing customers on how to use the tablets
Customers | Went well | Newsletter sign ups | 78% of customers signed up for the newsletter on the tablet | Include promotions and discounts in the newsletter, and give customers an incentive to subscribe to the newsletter
Customers | Needs improvement | Ease of use | Less than 50% of the customers found using the tablet and ordering from the tablet easy | Create simple, straightforward instructions for navigating and ordering through the tablets and place them on the tables.
Customers | Needs improvement | Wait time for getting a table | Over 50% of customers waited more than 15 minutes to seat at a table | Improve average table turn time by reducing the time it takes for customers to receive their order
Customers | Needs improvement | Order accuracy | 28% of customers responded that the kitchen didn't prepare their order properly, which is far from the 98% accuracy target | Highlight the importance of following customer special requests regarding their orders.
Customers | Needs improvement | Payment process | Customers reported that the tablet check-out process doesn't allow cash payments | Include cash payments as an option in the tablet check-out
Customers | Needs improvement | Technical functionality | 12% of customers reported technical issues, such as glitches or the screen freezing, which is over the less than 5% target | Contact Seydou and Terrific Tablets to discuss how to fix this
Customers | Needs improvement | Hybrid service | Some customers want the option of choosing a waiter, while 30% would like a mix of tablet ordering and waiter interaction | Redesign processes to include the option to have interaction with waiters when it comes to ordering
Project team | Went well | Tablet installation and configuration | All the tablets have been installed and are working at North and Downtown locations | Based on customer feedback, start planning the installation and configuration of tablets in other Sauce & Spoon locations
Project team | Went well | Flow of orders to the kitchen | Tickets flow was smooth, it came through at a good pace to the kitchen, and were easy to keep track of | Discuss the helpful updates that have been implemented to the kitchen operations
Project team | Went well | Handling of technical issues | Seydou and team were able to quickly identify, address and fix POS integration process issues | Update the process manual so that the solution is easy to find next time that issue comes up
Project team | Went well | Vendor communication | The weekly calls with vendors helped us stay on track and clarify task dependencies | For future projects, consider implementing weekly calls with vendors
Project team | Went well | Customer survey | The survey was able to capture meaningful data, and the results indicate that we met most of our customer satisfaction standards | Continue implementing what worked, focus on improving based on customer feedback, and continue surveying customers to keep finding improvement opportunities and identifying what works
Project team | Needs improvement | Table turn time | Table turn time didn't decrease as wanted in both locations | Peta will make a recommendation that they keep this cadence for the next series of rollouts
Project team | Needs improvement | Orders sent back | Not as many as before, but there were still some food orders that got sent back | Peta to prioritize this issue for further analysis
Project team | Needs improvement | Birthday club sign-ups | Only 16% of customers signed up for the birthday club | Seydou is proactively working to grow the participant list, and also working with the designer to update the content on the website and the tablets so it’s clearer what the program is, what we’re asking, and how people can participate.
Project team | Needs improvement | Internal operational issues | As we started implementing the tablets and training, we discovered a few internal operational issues that impacted the team’s ability to carry out tasks smoothly | For the next rollout, do a better job of understanding each location’s history before planning gets underway
Project team | Needs improvement | Tablet implementation timeline | Tablet implementation took a little bit longer than hoped for, since there was some vacation time that was unaccounted for | Make sure we plan things properly based on everyone’s availability
Project team | Needs improvement | Back of house capacity | The back of house staff is not currently prepared to handle a larger volume of orders | Help the back of house staff scale up their operations before the main launch
Project team | Needs improvement | Understanding of processes | There’s a lack of understanding between what the front of house staff and the back of house staff do | Take time to share front of house and back of house experiences
Project team | Needs improvement | Waitstaff training process | The training wasn't comprehensive enough, since it solely focused on tablet use | Develop a more comprehensive training session and take the opportunity to address other aspects of daily service operations in addition to how to use the tablets